## Sheet1
| PBI | PBI Description | Size | Tasks (Red is blocked) | Not Started | In Progress | Complete
1 | CPL Remainder Round | As an election officialI want the remainder round of the CPL method to be correctSo that we don’t need to recalculate everything by hand again to ensure the correctness | Small | Generate Unit Test Cases |  |  | Cuong Ha
|  | The final seats allocation must be intuitively reasonable when we, the election officials, look at the intermediate information (e.g., the remaining votes of each party, the current number of seats assigned to each party, the rank of each party, etc.) |  | Implement Unit Tests |  |  | Cuong Ha
|  | The remaining seats are allocated to each party one by one according to their current rank. If the remaining seats are less than the number of parties that have the same rank, a tie breaker must be performed. If every party has been given a seat and there are still some seats left, the system needs to go back and allocate them from the highest rank to lowest rank rather than giving all to the last visited party.Software compiles without errorAll unit tests passAll system tests passAll tests are documentedAll changes are documented in doxygenAll changes are documented with in-code documentationAll altered files have comment header updated |  | Document Unit Tests |  |  | Cuong Ha
2 | Date Input | As an election official I want to be able to enter the date of the audit file in any format So that we don’t need to compromise with just one format and therefore can take that off the training list | Small | Add error handling for improper date formats |  |  | Brian Bianchi
|  | When we, the election officials, enter a date, for example 01.01.2023 or 01/01/2023, we can view and read the content of the audit file with the correct date. |  | Generate Unit Test Cases |  |  | Brian Bianchi
|  | The system takes in a date in any format and creates an audit file with the date format “MM_DD_YYYY”. Software compiles without error All unit tests pass All system tests pass All tests are documented All changes are documented in doxygen All changes are documented with in-code documentation All altered files have comment header updated |  | Implement Unit Tests |  |  | Brian Bianchi
|  |  |  | Document Unit Tests |  |  | Brian Bianchi
3 | Multiple File Selection | As an election official I want to be able to select multiple files to compute the results of one election from So that ballot files from multiple polling places can be input | Small | Design discussion |  |  | Andrew Brevick
|  | The program supplies the option to choose multiple files. These files can have different names and be in different places. The user can choose just one file or they can choose several. |  | Update CLI and Controller flow logic |  |  | Andrew Brevick
|  | The UI (both GUI and CLI) allow the user to opt to choose more files to input into the system. These file paths get stored in a file path array for access by other parts of the system. Software compiles without error All unit tests pass All system tests pass All tests are documented All changes are documented in doxygen All changes are documented with in-code documentation All altered files have comment header updated |  | Update CLI display |  |  | Andrew Brevick
|  |  |  | Generate Unit Test Cases |  | Andrew Brevick
|  |  |  | Implement Unit Tests |  | Andrew Brevick
Document Unit Tests
4 | Multiple File Header Read IR | As an election official I want to input header data from multiple IRV election files So that we can bring in different files from multiple balloting locations | Small | Update IR header reading logic |  |  | Cuong Ha
|  | The files containing ballots information from more than one balloting location can be imported into the system for tabulating. When multiple file paths are entered manually, the system can read in ballot information from each file. |  | Generate Unit Test Cases |  |  | Cuong Ha
|  | The total ballots count are summed from different files, so the total ballots count must not be less than the total ballots count of one file. Software compiles without error All unit tests pass All system tests pass All tests are documented All changes are documented in doxygen All changes are documented with in-code documentation All altered files have comment header updated |  | Implement Unit Tests |  |  | Cuong Ha
|  |  |  | Document Unit Tests |  |  | Cuong Ha
5 | Multiple File Header Read CPL | As an election official I want to input header data from multiple CPL election files So that we can bring in different files from multiple balloting locations | Small | Update CPL header reading logic |  | Brian Bianchi
|  | The files containing ballots information from more than one balloting location can be imported into the system for tabulating. When multiple file paths are entered manually, the system can read in ballot information from each file. |  | Generate Unit Test Cases |  | Brian Bianchi
|  | The total ballots count are summed from different files, so the total ballots count must not be less than the total ballots count of one file. Software compiles without error All unit tests pass All system tests pass All tests are documented All changes are documented in doxygen All changes are documented with in-code documentation All altered files have comment header updated |  | Implement Unit Tests |  | Brian Bianchi
Document Unit Tests
8 | IR Summary Table | As an election official I want to see an IRV summary table that looks like the Wikipedia format So that I can easily see what happened each round | Large | Summarize wikipedia format as pseudocode |  | Andrew Brevick
|  | A table is shown with IRV round data The display table matches the format of the wikipedia table (excluding write-ins) The table is sized according the the number of rounds in a given election |  | Code table generation |  | Andrew Brevick
|  | A table is generated in proper format with IRV round data All unit tests pass All system test pass Edge cases regarding names and large numbers of data are handled |  | Generate Unit Test Cases
Implement Unit Tests
Document Unit Tests